## Sheet1
Index | Risk Description | Evaluation | Responsible Party | Probability | Impact | Risk Factor | Control Measures | Response Measures | Associated User Stories
1 | Customer data breach from outside org | financial loss to customer and/or business, regulatory issues, loss of customer trust | Devs | 3 | 5 | 15 | Require password in order to access database. Create private network so db can only be accessed via VM | Inform customer of issue, inform authorities, review security measures in app
2 | Data breach/fraud from within organisation | financial loss to customer and/or business, regulatory issues, loss of customer trust | Devs | 1 | 5 | 5 | Create user system which logs when/by who data was accessed. | Inform customer of issue, inform authorities, identify the culprit
3 | Loss of data due to hardware failure | financial loss to business, lost time due to need to manually control inventory, potential lost customers/customer trust | Devs | 1 | 5 | 5 | Use cloud resources with redundancy to store all data. | Clone data from backup
4 | Data wrongly stored/alterd due to user error | financial loss due to missed/incorrect orders being processed,loss of customers due to orders not reaching customers | Users/Devs | 2 | 3 | 6 | Ensure user documentation is complete and accurate | Ensure customer orders are resent correctly. Apologise to customers. Ensure staff are well trained to use software.
5 | Loss/corruption of data due to software failure | financial loss to business, lost time due to need to manually control inventory, potential lost customers/customer trust | Devs | 2 | 5 | 10 | Ensure there is a back-up of the all data. Ensure high test coverage before app goes live. | Clone all data from backup
6 | Order placed that exceeds stock | customer is inconvienienced, lost customers | Devs | 2 | 3 | 6 | Ensure software tracks stock levels and informs user that order cannot be fulfilled when erroneous order is created | Inform customer order cannot be filled. Review orgs buying policies to make sure stock held can satisfy demand
7 | Cloud services to mitigate 1-4 above are over-specced | orgs money wasted | devs | 1 | 2 | 2 | Create VMs and servers with appropriate resource levels | Regularly review cloud usage to ensure resources match traffic
8 | User accidentally deletes data | Has to be re-entered to the db, could potentially result in loss of customer etc. | devs/users | 2 | 3 | 6 | Add an warning prompt to any delete methods to ensure the user is sure they want to delete an item | Re-enter data if it is locally available elsewhere, contact customer/supplier if this is not the case.